## CYPS Delivery Plan 25-28
High Strategic Level Theme | Strategic Executive & Departmental Priority | Actions associated with Strategic Executive & Departmental Priorities | CYPS Outcome(s) | Area(s) of Greatest Focus | Lead Dept | Collaborating Partner(s) | Pooling and Sharing Resources | Planned duration of Action and Target date
Children in Care | Reform of children's social care services | Under the Children's Social Care Services Strategic Reform Programme, Departments, their respective agencies and voluntary and community sector organisations are working together to implement recommendations from the Independent Review of Children's Social Care Services, including; • The establishment of a multi-agency ‘front door’ for children’s services; • Resetting the relationship between the statutory and voluntary and community sectors towards greater collaboration and mutual support; and • The delivery of a new approach to supporting families across a continuum of need. | A, C,D, G | 14, 9, 19, 3, 6, 1, 7, 21 | Department of Health (DoH) | HSCTs, DOJ, DE, DfC | Yes | 5 years
Children in Care | Departmental Priority - underpins joint working between DoH and DE on the A Life Deserved: A Strategy on 'Caring for Children & Young People in Northern Ireland | Delivery of key projects to support children and young people with care experience. These are: • EA Primary Children Looked After Support Service; • Fostering Achievement – Educational Attainment of Children in Foster Care (delivered via DoH); • Mentoring Project – Mentoring Support for Looked After Children (delivered through DoH) | A, C, D, E, F, G | 9 | Department of Education (DE) | DoH, EA, Schools | Yes | Ongoing - annual reporting
Climate Change | Ministerial Priority 1 - Tackling Climate Change Together | Tackling Climate Change. Key actions will include; 1) Development and implementation of Northern Ireland’s first Climate Action Plan (CAP) with the aim, via the carbon budgeting process and by development and implementing supporting policies and proposals for emissions reductions, of working towards achieving the net zero target by 2050 (Patrick Savage). 2) Bring forward an updated Green Growth Strategy for Executive consideration (Michael Moorhead). | E, G E, G | 5, 7, 16, 19 5, 7, 16, 19 | Department of Agriculture, Environment and Rural Affairs (DAERA) | All NICS government departments, Youth Forum, Youth Assembly, NICCY, CAFRE, RSPB Youth EA - hosting of Youth Focus Groups. | No Yes | Ongoing as the Green Growth Strategy matures
Climate Change | Ministerial Priority 1 - Tackling Climate Change Together | ...cont. Tackling Climate Change. Key actions will include; 3) Publish the Third Northern Ireland Climate Change Adaptation Programme (NICCAP3) which sets out the actions departments and key stakeholders will take to create a climate resilient Northern Ireland (John Early). 4) Support the development and delivery of climate change awareness resources for schools and community youth groups (John Early). 5) Develop regulations that will establish the Just Transition Commission as required by the Climate Change Act (Northern Ireland) 2022. The Act makes it a legal requirement for the "youth group" to be represented on the Commission (Ian Fleming). | E, F C, E, F E, F, G | 5, 7, 16, 19 5, 7, 16, 19 5, 7, 16, 19 | Department of Agriculture, Environment and Rural Affairs (DAERA) | The NICCAP3 sets out details of policies, proposals and plans from all Departments and a range of key stakeholders. Keep Northern Ireland Beautiful (KNIB) All NICS Government departments, NICCY, Youth Form, Youth Assembly Education authority, Youth Assembly, Young farmers club of Ulster | No No No | Upon publication the NICCAP3 will cover 5 year period. Current project with KNIB runs to Dec 2026 in advance of which it will be reviewed. The Regulations to establish the Commission are expected to be brought to the AERA Committee and the Assembly for debate and approval during the spring of 2026 following which a recruitment process to appoint members, including a youth group representative, to the Commission will commence. The Commission will be established as a permanent body with an ongoing advisory role.
Early Intervention | Safer Communities/ To engage with our partners to help build safe and resilient communities, improve community relations and tackle paramilitary activity. | Deliver initiatives under the Executive Programme on Paramilitarism and Organised Crime to assist children and young people under threat of paramilitary intimidation or recruitment. Actions will include: • Continue to support the Probation Board ‘Aspire’ Programme. • Fund Youth Outreach Workers in areas where young people are vulnerable to paramilitary influence; • Support the use of diversionary activities and promote lawfulness within schools so that young people are less susceptible to paramilitary influence; • Develop bespoke interventions with statutory, voluntary and community sector partners to support young people at risk of or subject to paramilitary intimidation; • Deliver educational support in areas which are significantly impacted by social and economic deprivation and where there is significant paramilitary activity. | D | 13 | Department of Justice (DoJ) | Probation Board for NI, Safeguarding Board for NI, Education Authority, TEO, DoH, DfC, DE, PSNI | Yes | The mandate for the Executive Programme on Paramilitarism and Organised Crime comes to an end in March 2027. Consideration is currently been given to a review of its activity, including work with young people, in order to inform the Executive's response to paramilitarism after that date.
Early Intervention | Safer Communities: Continue to implement the Strategic Framework for Youth Justice to ensure the youth justice system improves outcomes for children, families, victims, and communities affected by crime. | Deliver against the five year Strategic Framework for Youth Justice (SFYJ) Action Plan, to ensure the youth justice system improves outcomes for children, families, victims, and communities affected by crime. Actions will include: • Working collaboratively with other statutory and third sector partners to help children avoid entering, or moving further into, the formal justice system. • Improving outcomes for children experiencing court through measures to aid understanding and simplify the sentencing framework. • Introducing legislative and operational reforms aimed at making custody a last resort for children, and improving transition between services. • Exploring reform of wider systemic issues, in the best interests of children | D | 11 | Department of Justice (DoJ) | PSNI, PPS, PBNI, NICTS, LCJO, DoH, HSC Trusts, DE, EA, DfC, DfE | No | March 2027
Early Intervention | Safer Communities/Addressing Harm and Vulnerability: | Supporting young people in contact with the law and youth justice system. Actions will include: • Becoming more responsive to trauma and mental health needs in practice. • Further development of Earlier Stage Diversion Services (ESDS) for children and young people at the early stages of coming into conflict with the law. • Embedding participation practice across the Youth Justice Agency and further develop a network of participation champions to ensure the meaningful involvement of children, families and victims in the design and delivery of our services and practice. | A, D | 5, 11 | Department of Justice (DoJ) | PSNI, PPS, PBNI, NICTS, DoH, HSC Trusts, DE, EA, DfC, DfE | Yes | 3 years to 31 March 2028
Early Intervention | Delivery of Northern Ireland Executive Early Learning and Childcare Strategy (In line with PfG Commitment) | Finalisation of Early Learning and Childcare Strategy (Subject to Executive Agreement) Public Consultation on ELCS Adoption and delivery of Early Learning and Childcare Strategy. | A, B, C | 5 | Department of Education (DE) | All NICS Departments. Delivery will also involve work from the wider public sector and support from the Community and Voluntary sector. | Yes | Ongoing
Early Intervention - Health and Wellbeing | Northern Ireland Food Strategy Framework. (PfG Shaping a Better Tomorrow: People Mission) | The cross-department Northern Ireland Food Strategy Framework draft Action Plan places significant early focus on Children and Young People, with an aim to embed foundations for a healthy lifelong relationship with food. A number of actions are identified, with assigned departmental ownership for delivery by June 2027. The associated Action Plan was published in May 2025. | A, C | 2 | Department of Agriculture, Environment and Rural Affairs (DAERA) | Department of Education, Department of Health, The Education Authority, The Public Health Agency, Food Standards Agency | Yes | 24 months and June 2027
Emotional Health and Wellbeing | Executive Priority - Contributes to the People Mission: Working to support everyone at all stages of their life to ensure they have the chance to succeed by improving life opportunities | Continued implementation and embedding of the joint Department of Education / Department of Health Children & Young People’s Emotional Health and Wellbeing in Education Framework. Projects currently delivered under the framework include: Emotional wellbeing Team in Schools (DoH SPPG); RISE NI Key Stage 2 (PHA); REACH (EA Youth Service); Being Well Doing Well (EA). The Framework also contributes funding to The Attach Programme, part of the EA's Primary Children Looked After Advisory Service. | A, B, C, D, F, G | 5 | Department of Education (DE) | DoH, PHA, EA, EA Youth Service, Schools | Yes | Ongoing - annual reporting
Health and Wellbeing - Active Travel | Draft PfG 2024-27 & DfI Strategic Framework-facilitating Active Travel Options | Deliver Practical Child Pedestrian Safety Training via a three-year rolling training scheme for children in year 3 to year 5 (6-9 year olds). To do this we will: • Provide schools with intensive support over the course of the programme to ensure knowledge, skills and understanding are embedded. • Encourage and equip children to enable them to make responsible road safety and active travel choices both now and into the future. Note: Increased active travel will assist children to meet the Chief Medical Officer’s target of 60 minutes physical activity per day. • Use the scheme to encourage the schools to promote its objectives to parents to use sustainable means of travel. Offer the Cycling Proficiency Scheme to all primary and special schools across Northern Ireland. To do this we will: • Use the scheme to teach children a lifelong skill and provide them with the confidence to cycle safely and identify risks they may come across on the roads. • Encourage children to choose a more sustainable and active travel option as they progress into adulthood. | A, B, C, D | 2, 5, 7 5, 16 | Department for Infrastructure (DfI) | Schools | Yes | 2024-2028
Health and Wellbeing - Active Travel | Draft PfG 2024-27 & DfI Strategic Framework-facilitating Active Travel Options | Deliver the Active School Travel programme to new schools each year to encourage and influence children to travel more actively to school (cycling, walking, scooting, skating or ‘park and ride, stride, scoot’). Embedding knowledge of the benefits of choosing to travel more actively will provide children with the foundation for life skills that will enable them to increase levels of physical activity and safely choose active travel options and, in doing so, help reduce reliance on private cars, lessen traffic congestion and improve the environment. | A, B, C, D | 4, 5, 16 | Department for Infrastructure (DfI) | Schools / Public Health Agency / Contractor | Yes | 2024-2026 (current contract = 20 months: 01/01/25-31/08/26)
Post-16 Education | Ministerial Priority | To take forward legislation in this Assembly mandate which would require young people to continue in their education or training until age 18 | C | 7, 8, 9, 10 | Department of Education (DE) | DfE, DfC, DoH, DAERA, CAFRE, EA, CCMS, Boards of Governors of VG and GMI Schools. | Yes | March 2027
Post-16 Education | 14-19 Framework | The 14-19 Framework includes 34 actions to ensure young people have the skills and knowledge to enable them to succeed as individuals, as contributors to society and to the Northern Ireland economy. These are being progressed collaboratively under three thematic groups, namely Post 16, Curriculum and Qualifications and Careers working groups supported by a jointly resourced Project Management Office. | C, E, F | 4 | Department of Education (DE) and Department for the Economy (DfE) | DfE, NISCA, EA, CCEA | Yes | 3-5 years
Post-16 Education | Raise Productivity | Deliver impartial careers advice and guidance to young people at key transition stages including providing additional support to those with barriers. | C, F | 4 | Department for the Economy (DfE) | DE, EA, HSCT, YJA,EWS | No | Ongoing
Post-16 Support | Together Building a United Community Strategy - United Youth Headline Action | United Youth Programme (part of TBUC Strategy, delivered via PEACEPLUS Youth Programme) | C, F, H | 4, 7, 13 | Department for the Economy (DfE) | SEUPB, TEO, Irish Department DCEDIY, FE college, voluntary and Comminity organisations | No | April 2024-March 2028
Safeguarding | Safer Communities/Addressing Harm and Vulnerability: Implementation of the Gillen Review recommendations aimed at improving the experience of child victims of serious sexual offences. | Implementation of the Gillen Review recommendations aimed at improving the experience of child victims of serious sexual offences. Actions will include: • Continuing to deliver the judge-led voluntary protocol in Belfast and Antrim Crown Courts in qualifying cases. • Continuing to deliver the Child Sexual Offences Legal Adviser (CSOLA) pilot scheme, which launched in February 2025 and runs until 31 March 2027. • Continuing to provide Remote Evidence Centres for child witnesses in Belfast, Craigavon and Foyle and provide recommendations for the further roll-out of remote evidence facilities across Northern Ireland by March 2026. • Scoping and costing options for a Barnahus model for Northern Ireland. • Developing arrangements for a pilot to test pre-recorded cross-examination in cases involving children under 13 years old in Belfast. | D, G | 14 | Department of Justice (DoJ) | PSNI, Public Prosecution Service, Judiciary, NICTS, Victim Support NI, NSPCC, DoH | No | March 2027
Safeguarding | Safer Communities | Work with Departments and other statutory agencies and sectors to implement actions within the Child Criminal Exploitation (CCE) action plan to address child criminal exploitation. Examples of actions include: • agreeing a definition and accompanying narrative for CCE, in the context of a continuum of child exploitation and abuse, and ensuring relevant strategies, policies, procedures and guidance are updated accordingly. • A child and young person friendly version of the definition and associated materials will also be developed. In addition the plan seeks to make any enhancements necessary to existing multi-agency Child Protection arrangements (health, social services, education, local councils, Housing Executive, YJA, PPS, PSNI, SBNI etc.), to ensure that, from a safeguarding perspective, the criminal exploitation of children is recognised and addressed using a trauma-informed, multi-agency approach to reduce vulnerability and support victims and their families, alongside the pursuit of those involved in exploiting children and young people. | A, D | 4, 11, 13, 14 | Jointly led by: 1) Department of Health (DoH), 2) Department of Justice (DoJ) & 3) Department of Education | DoJ, DoH, DE, TEO, DoF, SBNI,EA, HSCTs, PSNI | Yes | 2 years
Safeguarding | Implementation of the Domestic and Sexual Abuse Strategy which aligns with Ending Violence Against Woman and Girls | In partnership with the Department of Justice oversee the implementation of actions within the Domestic and Sexual Abuse Strategy Action Plan. Actions will include: • Continuing to hear and respond to children experiencing domestic abuse, through the delivery of the Domestic Violence and Abuse Committee's workplan. • Promoting knowledge, awareness and resources in relation to harmful sexual behaviour amongst front-line professionals. • Rolling out Operation Encompass to non-statutory Pre School Education Providers and voluntary nurseries. (Lead: DE, DoH Partners: PSNI, HSCTs, EA.) | A, D | 3, 5, 14 | Department of Health (DoH) | DoJ, DfC, DE and TEO | Yes | Target date for implementation of strategy is 2031.
Safeguarding | Safer Communities | Online Safety Strategy - implement actions to empower children and young people, parents/carers and those working with children and young people to recognise, prevent and respond to abusive behaviours online. Actions will include; • The development and dissemination of sample online safety procedures to support embedding of online safety within organisations; and • The review of current inclusion of online safety content within third level education training courses where students will eventually work with children, young people or parents/carers. | A, D | 12 | Department of Health (DoH) | All Government Departments, SBNI. | Yes | Target date for implementation of the strategy is April 2027
Safeguarding | Departmental Priority - underpins the safety and wellbeing of CYP in education | Safeguarding of Children and Young People in Education – ensuring that education settings do whatever is reasonable and required by legislation to safeguard and promote their pupils safety, welfare and protect the children and young people in their charge from harm. Some actions that are currently linked to this are: EA Child Protection Support Service; Safer Schools App; development of Guidance for Education Settings | A, D, G, H | 12, 13, 14, 15 | Department of Education (DE) | DoH, SBNI, EA, Schools | No | Ongoing - annual reporting
Safeguarding | PfG commitment & TEO Ending Violence Against Women and Girls Strategic Framework | • Deliver in partnership with the Department of Education (DE) an agreed EVAWG action plan to coordinate interventions targeted at children and young people and focused on healthy relationships, delivered with early years providers, schools and community groups, parents and carers. • Partner with the Department of Education and the Education Authority Youth Services to embed a diverse youth voice in the EVAWG programme through integration of EVAWG into curriculum, youth leader training and Youth Voice structures. • Develop and deliver an EVAWG action plan through the Tertiary Education forum | A, D | 2, 20, 22 | The Executive Office (TEO), Department of Education (DE) Department for the Economy (DfE) | DE, DoH, DoJ, DfE, EA, Councils, Community and Voluntary Sector |  | 2024 - 2026, current delivery plan
Special Educational Needs and Disabilities | Special Educational Needs | Subject to funding, we will implement the Special Educational Needs (SEN) Reform Delivery Plan to ensure that children and young children with SEN have access to the right support, by the right people, at the right time and in the right place while providing support for families. | C | 8 | Department of Education (DE) | DE, EA, ETI, DoH, PHA, CCEA, CCMS, Middletown Centre for Autism, HEIs, DfE, Community & Voluntary Sector | TBC | 5 years: March 2030
Special Educational Needs and Disabilities | The Department for Communities is fully committed to supporting all people with disabilities and health conditions, progress towards, move into and stay in employment. | Supporting young people with disabilities and health conditions, progress towards, move into and stay in employment. Actions include: • Continue to support young people with disabilities in work • Deliver Access to Work (NI) and Workable (NI) to those who need support in work • Continue to work with Department of Health and Employers on the role of the Condition Management Programme to help people manage their health condition in work; Further information is available on Workable (NI) Access to Work (NI) and the Condition Management Programme. Continued support for young people to progress towards and move into employment through the Work Experience Programme (WEP) and through the development of a new employability programme which will remove barriers to economic activity (awaiting approvals). | E | 4, 7 | Department for Communities (DfC) | 5 Health Trusts across Northern Ireland, Several providers in the Voluntary and Community Sector | No | Ongoing
Tackling Poverty and Disadvantage | Delivery of Northern Ireland Executive Anti-Poverty Strategy (In line with PfG Commitment) | Finalisation of Anti-Poverty Strategy (Subject to Executive Agreement) Public Consultation on APS Adoption and delivery of Anti-Poverty Strategy. | E | 7 | Department for Communities (DfC) | All NICS Departments. Delivery will also involve work from the wider public sector and support from the Community and Voluntary sector. | No | Ongoing
Tackling Poverty and Disadvantage | Tackling Educational Disadvantage | Tackle educational disadvantage through collaborative place based education in the community initiatives. This includes DE WRAP (Thrive, Eastside Learning, Forward South STEP and Greater Shantallow Area Partnership) as well as initiatives in North and West Belfast. Delivery of the RAISE programme, which aims to raise aspiration and reduce educational disadvantage. (RAISE is a whole community, place-based approach in 18 localities across Northern Ireland.) | C | 7 | Department of Education (DE) | Thrive, Eastside Learning, Greater Shantallow Partnership, Forward South Member of the RAISE Programme Board - All NICS Departments | Yes No | Completion March 2027 2025 to 2027
Youth Homelessness | Supporting People Strategic Plan and Covid-19 Recovery Plan 2022-2025 | Continue to deliver the Supporting People Programme. This includes; • Implementing findings from the Review of Jointly Commissioned Supported Accommodation Projects; and • Developing models of support for young people experiencing homelessness including improved emergency accommodation options, Housing First, Nightstop and shared tenancies. (The achievement of actions to develop models of support requires additional funding and is subject to DfC budget confirmation). | B, C, D, E, F | 4,7,11 | Department for Communities (DfC) | NIHE, SPPG, DoH, DoJ, PBNI, SP Providers | No | 2022 - 2026
Youth Homelessness | Homelessness Prevention | The Housing Executive has developed a Youth Homelessness Action Plan (published in November 2024) which is targeted to groups of young people particularly at risk of becoming homeless. Including: • Young people who have been part of the care system prior to reaching 16 years of age, and then become homeless at a later point. • Young people aged 16/17 years, not known to Social Services or who do not have care experience in their background, and present as homeless. • Young people aged 18-25 years, who present to the Housing Executive as homeless. The Housing Executive is working collaboratively with statutory sector partners to develop a strategic programme, called ‘New Foundations’, to assist young people leaving care through lasting ‘systems change’ to prevent homelessness among this important group. | D | 4 | Department for Communities (DfC) | NIHE, DoH, YJA NIHE, DoH, DfE, YJA, Probation, TEO | No | 2024-2027 2025 - 2027